## Sheet1
Project_Type | Vendor_Reliability | Training_Quality | Stakeholder_Engagement_Level | Complexity_Score | Team_Size | Budget_Planned_K | Timeline_Months_Planned | Original_Risk_Description | Original_Category | Likelihood | Impact | Triggers | Mitigation | Escalation_Probability_% | Predicted_Escalation | Manual_Risk_Score | Risk_Level | Score_Discrepancy
Predictive_Analytics | Medium | Medium | High | 5.9236 | 15 | 550 | 11 | Delays or failures in integrating ReadmitPredict dashboard with current EMR system. | Technical | 4 | 5 |  |  | 63.4385 | 1 | 20 | Medium | -16.5615
Predictive_Analytics | Medium | Medium | High | 4.8521 | 15 | 550 | 11 | Model may produce inaccurate risk scores for rural and minority patient groups | Ethical | 3 | 4 |  |  | 60.6753 | 1 | 12 | Medium | 12.6753
Predictive_Analytics | Medium | Medium | High | 4.696 | 15 | 550 | 11 | Clinicians resist using the new dashboard due to added workflow steps. | Operational | 4 | 4 |  |  | 61.0106 | 1 | 16 | Medium | -2.9894
Predictive_Analytics | Medium | High | High | 6.296 | 15 | 550 | 11 | Changes to CMS HRRP rules (e.g., pneumonia reinstatement) affect tool validation or penalty calculations. | Regulatory | 3 | 5 |  |  | 37.6039 | 0 | 15 | Low | -22.3961
Predictive_Analytics | Medium | Medium | Medium | 2.4681 | 15 | 550 | 11 | Budget overrun due to unexpected cloud computing or consulting costs. | Financial | 3 | 4 |  |  | 63.6084 | 1 | 12 | Medium | 15.6084
Predictive_Analytics | Medium | Medium | High | 3.868 | 15 | 550 | 11 | Data security breach during cloud-based real-time scoring. | Technical | 2 | 5 |  |  | 59.3958 | 0 | 10 | Medium | 19.3958
Predictive_Analytics | Medium | Medium | Medium | 2.1743 | 15 | 550 | 11 | Staff turnover delays training and knowledge transfer. | Operational | 4 | 3 |  |  | 63.4672 | 1 | 12 | Medium | 15.4672
Predictive_Analytics | Medium | Medium | High | 4.5985 | 15 | 550 | 11 | Over-reliance on tool leads to reduced clinical judgment. | Ethical | 3 | 4 |  |  | 60.4835 | 1 | 12 | Medium | 12.4835
Predictive_Analytics | Medium | Medium | Medium | 3.8033 | 15 | 550 | 11 | Pilot shows lower-than-expected readmission reduction, risking full rollout approval. | Financial | 3 | 4 |  |  | 59.0954 | 0 | 12 | Medium | 11.0954
Predictive_Analytics | Medium | Medium | High | 5.5242 | 15 | 550 | 11 | Performance lag in dashboard during peak hours. | Technical | 4 | 3 |  |  | 63.591 | 1 | 12 | Medium | 15.591
Predictive_Analytics | Medium | Medium | High | 2.5618 | 15 | 550 | 11 | Nurses and physicians find the dashboard too time-consuming during discharge planning. | Operational | 4 | 4 |  |  | 67.2018 | 1 | 16 | High | 3.2018
Predictive_Analytics | Medium | Medium | High | 6.3097 | 15 | 550 | 11 | Inconsistent real-time scoring due to intermittent cloud connectivity issues in the hospital. | Technical | 3 | 4 |  |  | 62.0902 | 1 | 12 | Medium | 14.0902
Predictive_Analytics | Medium | Medium | Medium | 4.4973 | 15 | 550 | 11 | Unexpected licensing or subscription cost increases from cloud provider or ML platform. | Financial | 3 | 4 |  |  | 58.6161 | 0 | 12 | Medium | 10.6161
Predictive_Analytics | Medium | High | High | 4.387 | 15 | 550 | 11 | Audit or compliance review uncovers gaps in data handling documentation. | Regulatory | 2 | 5 |  |  | 39.6509 | 0 | 10 | Low | -0.34913
Predictive_Analytics | Medium | Medium | High | 2.5455 | 15 | 550 | 11 | Risk scores systematically underestimate readmission risk for patients with limited English proficiency. | Ethical | 3 | 4 |  |  | 67.2018 | 1 | 12 | High | 19.2018
Predictive_Analytics | Medium | Medium | High | 3.0502 | 15 | 550 | 11 | Insufficient follow-up resources for high-risk patients flagged by the tool. | Operational | 4 | 4 |  |  | 58.7027 | 0 | 16 | Medium | -5.2973
Predictive_Analytics | Medium | Medium | High | 5.7127 | 15 | 550 | 11 | Data mapping errors lead to incorrect LACE component values pulled from EMR. | Technical | 4 | 5 |  |  | 63.7385 | 1 | 20 | Medium | -16.2615
Predictive_Analytics | Medium | Medium | Medium | 3.0743 | 15 | 550 | 11 | Pilot costs exceed budget due to extended training needs. | Financial | 3 | 3 |  |  | 55.6147 | 0 | 9 | Medium | 19.6147
Predictive_Analytics | Medium | Medium | High | 3.2958 | 15 | 550 | 11 | Misinterpretation of percentage-based risk scores leading to defensive medicine practices. | Operational | 3 | 4 |  |  | 60.8765 | 1 | 12 | Medium | 12.8765
Predictive_Analytics | Medium | High | High | 4.6237 | 15 | 550 | 11 | Delay in obtaining IRB/ethics approval for model validation using real patient data. | Regulatory | 3 | 4 |  |  | 37.7328 | 0 | 12 | Low | -10.2672