## Form Responses 1
Timestamp | Risk Category | Risk Description | Likelihood | Impact | Your Role/Department | Potential Triggers / Examples: | Mitigation Ideas:
2026-01-28 15:05 | Technical | Delays or failures in integrating ReadmitPredict dashboard with current EMR system. | 4 | 5 | IT | Vendor API changes mid-project, mismatched data formats between EMR and cloud tool, or incomplete test environments leading to mapping errors during pilot in Cardiology. | Conduct early API compatibility testing with vendor sandbox, allocate dedicated integration sprint in month 3, and involve IT and clinicians in joint UAT sessions.
2026-01-28 15:08 | Ethical | Model may produce inaccurate risk scores for rural and minority patient groups | 3 | 4 | Internal Medicine | Training data skewed toward urban hospital admissions, leading to higher false negatives in non-English speakers or low-income patients during Internal Medicine pilot. | Perform regular bias audits using fairness toolkits, augment dataset with diverse synthetic cases, and include equity review in every model update cycle.
2026-01-28 15:09 | Operational | Clinicians resist using the new dashboard due to added workflow steps. | 4 | 4 | Cardiology | Dashboard alerts interrupt rounding, or color-coded scores seem "black box" without clear explanations, causing distrust in high-volume Cardiology shifts. | Run clinician-led demo sessions and feedback loops pre-pilot, provide one-click "explain risk" feature, and offer CME credits for early adopters.
2026-01-28 15:11 | Regulatory | Changes to CMS HRRP rules (e.g., pneumonia reinstatement) affect tool validation or penalty calculations. | 3 | 5 | Compliance | 2026 policy update expands metrics, requiring quick model revalidation that delays rollout beyond 12-month timeline. | Build modular model architecture for fast retraining, subscribe to CMS alerts, and include contingency buffer (1-2 months) in schedule for regulatory adjustments.
2026-01-28 15:12 | Financial | Budget overrun due to unexpected cloud computing or consulting costs. | 3 | 4 | Finance | Higher-than-planned API calls during testing or need for extra data scientist hours to address bias issues, pushing past $550K cap. | Set monthly burn-rate tracking dashboard, prioritize open-source tools where possible, and negotiate fixed-price vendor contracts for integration phase.
2026-01-28 15:13 | Technical | Data security breach during cloud-based real-time scoring. | 2 | 5 | IT | Phishing attack on clinician credentials or misconfigured cloud access leading to unauthorized PHI exposure. | Enforce MFA and role-based access, conduct quarterly penetration testing, and include HIPAA-compliant encryption in all data pipelines.
2026-01-28 15:15 | Operational | Staff turnover delays training and knowledge transfer. | 4 | 3 | Prefer not to say | Key IT integrator leaves mid-project or high nurse turnover in pilot departments reduces champion users. | Cross-train at least two people per role, create video walkthroughs and quick-reference guides, and build succession planning into project charter.
2026-01-28 15:17 | Ethical | Over-reliance on tool leads to reduced clinical judgment. | 3 | 4 | Cardiology | Clinicians defer to red alerts without reviewing full patient context, causing inappropriate discharge decisions. | Include mandatory "override reason" field with audit logging, emphasize tool as decision support only in training, and monitor override rates quarterly.
2026-01-28 15:20 | Financial | Pilot shows lower-than-expected readmission reduction, risking full rollout approval. | 3 | 4 | Finance | External factors (e.g., flu season spike) mask tool benefits, or insufficient follow-up interventions post-discharge. | Define clear success metrics upfront (e.g., >15% reduction in pilot), track leading indicators monthly, and prepare alternative ROI narratives for stakeholders.
2026-01-28 15:21 | Technical | Performance lag in dashboard during peak hours. | 4 | 3 | IT | Cloud latency when scoring multiple patients simultaneously in busy Internal Medicine unit. | Optimize queries and use caching, conduct load testing with simulated peak usage, and have fallback manual LACE scoring ready.
2026-01-28 15:22 | Operational | Nurses and physicians find the dashboard too time-consuming during discharge planning. | 4 | 4 | Internal Medicine | Adding extra clicks to review explanations or flags in an already busy workflow, especially during evening/night shifts in Internal Medicine. | Implement single-sign-on and auto-populate discharge notes with risk summary, conduct time-motion studies pre- and post-pilot, and prioritize mobile-friendly design for quick checks.
2026-01-28 15:23 | Technical | Inconsistent real-time scoring due to intermittent cloud connectivity issues in the hospital. | 3 | 4 | IT | Wi-Fi dead zones in older hospital wings or network congestion during peak hours causing delayed or failed risk score refreshes. | Add offline fallback mode using last-known LACE score, implement edge caching, and partner with IT for dedicated bandwidth allocation during pilot phases.
2026-01-28 15:24 | Financial | Unexpected licensing or subscription cost increases from cloud provider or ML platform. | 3 | 4 | Finance | Usage-based pricing spikes during high-volume testing or vendor price adjustment announced mid-project. | Lock in fixed-rate contract for first 18 months, monitor monthly usage closely with alerts at 80% of budgeted compute, and evaluate multi-cloud fallback options.
2026-01-28 15:25 | Regulatory | Audit or compliance review uncovers gaps in data handling documentation. | 2 | 5 | Compliance | Incomplete audit trail for model predictions or missing DPIA (Data Protection Impact Assessment) for ML processing of PHI. | Engage compliance officer from day one to co-develop documentation templates, automate logging of all model inferences, and schedule mock audit in month 4.
2026-01-28 15:26 | Ethical | Risk scores systematically underestimate readmission risk for patients with limited English proficiency. | 3 | 4 | Internal Medicine | Notes and social determinants data less complete or less coded for non-English-speaking patients, skewing comorbidity and acuity components. | Stratify performance metrics by language group, incorporate interpreter-translated notes in validation dataset, and add explicit language flag as a model input.
2026-01-28 15:27 | Operational | Insufficient follow-up resources for high-risk patients flagged by the tool. | 4 | 4 | Cardiology | Social work or case management teams already at capacity, so red-flag patients discharged without timely post-discharge calls or home health referral. | Create automatic referral triggers to care coordination team for red (>50%) patients, pilot dedicated discharge navigator role for high-risk cases, and track follow-up completion rate as a KPI.
2026-01-28 15:29 | Technical | Data mapping errors lead to incorrect LACE component values pulled from EMR. | 4 | 5 | IT | Different coding practices across Cardiology vs. Internal Medicine departments or legacy vs. current EMR fields causing misinterpretation of length-of-stay or comorbidity flags. | Build and maintain detailed data dictionary with clinician validation, run parallel manual LACE checks on first 100 cases, and implement automated data quality alerts.
2026-01-28 15:30 | Financial | Pilot costs exceed budget due to extended training needs. | 3 | 3 | Finance | Lower-than-expected clinician engagement requires additional in-person workshops or one-on-one coaching sessions beyond planned budget. | Start with virtual recorded modules and peer champions to reduce live training load, set training completion milestones tied to go-live, and track actual vs. planned hours weekly.
2026-01-28 15:32 | Operational | Misinterpretation of percentage-based risk scores leading to defensive medicine practices. | 3 | 4 | Internal Medicine | Clinicians interpret yellow (20–50%) as "safe to discharge" without reviewing factors, or red (>50%) triggers unnecessary extended stays/tests. | Include plain-language factor explanations and risk stratification guidance in dashboard tooltips, run scenario-based training simulations, and audit discharge decisions against scores quarterly.
2026-01-28 15:33 | Regulatory | Delay in obtaining IRB/ethics approval for model validation using real patient data. | 3 | 4 | Compliance | Committee requests additional safeguards for ML transparency or concerns about secondary use of historical readmission data. | Submit protocol early (month 2), prepare plain-language summary of model and bias mitigation plan, and have de-identified synthetic data ready as fallback for initial testing.